## Sheet1
Week # | To Do | Owned by | Deadline | Status | Comments
Done
Week 7 - THE GREAT REWRTING! | Prototype development | Jasfer | 2019-08-25 |  | Done
Notes: coming up with a plan of attack | Prototype testing | Jasfer | 2019-08-25 |  | Done
| Prototype fine tuning | Jasfer | 2019-08-25 |  | Done
| Prototype Field test | Jasfer | 2019-08-25 |  | Done
| Prototype Interview | Jerico | 2019-08-25 |  | Done
| Field Interview | Jerico | 2019-08-25 |  | Done
| Interview complilation | Jerico | 2019-08-25 |  | Done
| Review | Both | 2019-08-25 |  | Done
Week 8 - THE FINAL RETHINKING | Prototype Finalization | Jasfer | 2019-09-01
Notes: Post midterm revisition amd finalization of needfinding subject | Prototype interview Finalization | Jasfer | 2019-09-01
| Prototype | Jasfer | 2019-09-01
| Wireframe | Jasfer | 2019-09-01
| POV and User Needs | Jerico | 2019-09-01
| Skeleton system | Jasfer | 2019-09-01
| System and website | Jerico | 2019-09-01
| Submission | Both | 2019-09-01
Week 9 - THE INTERNET GALLORE | Pesudo code | Both | 2019-09-08
Notes: LOTS OF CODING! | Website 1 | Jasfer | 2019-09-08
| Website 2 | Jasfer | 2019-09-08
| Website 3 | Jerico | 2019-09-08
| Website 4 | Jerico | 2019-09-08
| Picking what is the best | Jerico | 2019-09-08
| Intergrating | Jerico | 2019-09-08
| Submission | Jerico | 2019-09-08
| UI improving | Jerico |  |  | Optional
| Decoration of website | Jerico |  |  | Optional
Week 10 - TESTERS ELECTRIC BOOGALOO | Develop user test plan | Jasfer | 2019-09-15
Notes: panicked coding | Create questionnaire for user testing | Jerico | 2019-09-15
| Run user tests | Both | 2019-09-15
| Produce formal updated plan of implementation with incorporated feedback | Both | 2019-09-15
2019-09-15
Week 11 - CODING ELECTRIC BOOGALOOO | G-cash implementation | Both | 2019-09-22
Notes: even more panicked coding | Complilationof data | Both | 2019-09-22
| Fine tuning of website | Both | 2019-09-22
| Beutification of website | Both | 2019-09-22
Week 12a - PREPARATION OF PRESENTATION | Work on website | Both | 2019-09-28
Notes: Final preparations | Fine tuning | Both | 2019-09-28
| Reviewing of data | Jerico | 2019-09-28
| Complication of whats needed | Jasfer | 2019-09-28
| Presentation and rehershal | Both | 2019-09-28
Week 12b -IDEA PRESENTAION | Panicked brainstorming |  | 2019-09-29
Notes: Final boss | Prayer |  | 2019-09-29
| 1-minute madness slide |  | 2019-09-29
Booth poster